## VIP
Inputs Worksheet
Program: | Volunteer Internship Program (One term)
Cycle: | Winter 2010
|  |  |  | Estimate |  |  | Actual |  |  | Resources Remaining
Resource Category | Resource | Details/Notes | Measure Required? | Total Hours | Total Dollars ($) | # Units | Total Hours | Total Dollars ($) | # Units | Total Hours | Total Dollars ($) | # Units
Facilities & Infrastructure | Interview Room | Room booked for two weeks for 6 hours per day | Yes | 60 |  | 1 | 76 |  | 2 | -16 | 0 | -1
Facilities & Infrastructure | LCD Projector | 27 one-hour sessions require the use of a projector (plus 15 minutes prior to each session for set-up) | Yes | 33.75 |  | 1 | 33.75 |  | 1 | 0 | 0 | 0
Facilities & Infrastructure | Workshop Room (351) | Workshops, MPRD's, and Presentations booked for a total of 39 hours plus 15 minutes before each of 37 sessions for set-up | Yes | 48.25 |  | 1 | 50 |  | 1 | -1.75 | 0 | 0
Funding | Revenue |  | Yes |  | 12500 | 125 |  | 11300 | 113 | 0 | 1200 | 12
Materials | Awards | Costs associated with the supervisor and student award | Yes |  | 100 |  |  | 100 |  | 0 | 0 | 0
Materials | CCE Breakfast | VIP contribution toward cost of annual event (prorated for term) | Yes |  | 1166.6667 |  |  | 1155.3333 |  | 0 | 11.3333 | 0
Materials | Folders | Folders are 28 cents each. Purchased 150 for term. | Yes |  | 35 | 125 |  | 39.48 | 141 | 0 | -4.48 | -16
Materials | Insurance Policy | $1.18 + tax per student per placement wk. Est. 120 for 10 weeks each | Yes |  | 1529.28 |  |  | 3850 |  | 0 | -2320.72 | 0
Materials | Printing costs | Includes printed program materials (est. 50 pages per student), carbon copy forms for contract and presentation, labels and and certificates. | Yes |  | 350 |  |  | 350 |  | 0 | 0 | 0
Materials | Workbooks | Based on invoice from Document Imaging. 150 printed. | Yes |  | 223.44 | 150 |  | 184.76 | 124 | 0 | 38.68 | 26
Staff | Applied Learning Coordinator | Estimated 50% of ALC's hours focus on VIP | Yes | 300 | 12000 | 1 | 325 | 13000 |  | -25 | -1000 | 1
Staff | CDS Secretary | Posted 135 jobs and takes about 7 minutes per job (5 min for re-post, 10 min for new) plus assistance with fee collection | Yes | 25 | 625 | 1 | 30 | 750 | 1 | -5 | -125 | 0
Staff | MSW Student Intern | Facilitation of 10 sessions (5 MPRD's and 5 Presenations) of one hour each with 15 minutes before and after for prep and close up | Yes | 15 |  | 1 | 15 |  | 1 | 0 | 0 | 0
Staff | VIP Program Assistant | 100% of VIP Asst focus on VIP | Yes | 260 | 2600 | 1 | 250 | 2500 |  | 10 | 100 | 1
Staff | VIP Selection Board | Allow for 240 interview spots (15 min each) with two interviewees and a 1 hour training session. | Yes | 130 |  | 10 | 130 |  | 10 | 0 | 0 | 0
Campus/Community | Job Postings |  | No | [6 empty] | 0 | 0 | 0
Campus/Community | President's Support | Signs certificate, attends breakfast | No | [6 empty] | 0 | 0 | 0
Campus/Community | Web Site |  | No | [6 empty] | 0 | 0 | 0
Facilities & Infrastructure | Computer and Laptop |  | No | [6 empty] | 0 | 0 | 0
Facilities & Infrastructure | Cubicle/Desk Space |  | No | [6 empty] | 0 | 0 | 0
Facilities & Infrastructure | Filing Cabinets |  | No | [6 empty] | 0 | 0 | 0
Facilities & Infrastructure | myCareer |  | No | [6 empty] | 0 | 0 | 0
Facilities & Infrastructure | Offices |  | No | [6 empty] | 0 | 0 | 0
Facilities & Infrastructure | Online Posting System |  | No | [6 empty] | 0 | 0 | 0
Facilities & Infrastructure | Phones |  | No | [6 empty] | 0 | 0 | 0
Funding | Base Budget |  | No | [6 empty] | 0 | 0 | 0
Materials | Certificates |  | No | [6 empty] | 0 | 0 | 0
Materials | Printed Forms and paperwork |  | No | [6 empty] | 0 | 0 | 0
Key Questions
How much staff resources are going in to running VIP each semester and what is it costing?
750 hours of staff time and $16250 is going into the staff resources of running the program.
What is the cost per student to run VIP?
Based on above, we can see that $21,930 is spent on VIP each term.
If we look at the per cost of students that actually confirmed participation and paid fee (yet, may have deferred prior of after) it is 130 students and the cost per student is therefore $169.69.
This includes both direct variable costs (insurance, printing and copying) and indirect costs (staff salary, employer breakfast). Further analysis could be done to determine direct costs only.
How much is VIP drawing on the workshop and interview rooms?
Roughly 126 hours of common rooms are booked for VIP activities each term, with 60% of the time being used for interviewing and 40% for workshops and activities.
Note on A5: Kerri Zold: Possible categories include: - Staffing - Facilities & Infrastructure - Materials - Funding - Campus/Community

## Template
Inputs Worksheet
Program:
Cycle:
|  |  |  | Estimate |  |  | Actual |  |  | Resources Remaining
Resource Category | Resource | Details/Notes | Measure Required? | Total Hours | Total Dollars ($) | # Units | Total Hours | Total Dollars ($) | # Units | Total Hours | Total Dollars ($) | # Units
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
Key Questions
Note on A5: Kerri Zold: Possible categories include: - Staffing - Facilities & Infrastructure - Materials - Funding - Campus/Community